## Establishment
Hazard Identification, Risk Assessment & Control Measures
Project: XXXXX |  |  | Section/Deptt.: Project Establishment | [5 empty] | Date:
S. No. | Activity | Hazards (Conditions/Act) | Risk | Severity (S) | Probability (P) | SXP | Legal (Y/N) | Risk Level (H, M or L) | Risk Category (A/UA) | Control Measures
1 | Project Office
a | Indoor Air Quality in Office area | Contaminated indoor air | 1. Possiblity of staff falling sick, specially staff with sinus problem 2. Lack of Concentration, 3. Low productivity | 3 | 2 | 6 | N | L | A |  | A mechanism to be developed for Air quality & illumination monitoring
b | Illumination in Office area | Improper (inadequate/ more) illumination | 1. Detrimental impacts on eyes 2. Lack of Concentration, 3. Low productivity | 3 | 2 | 6 | N | L | A
c | Ergonomics | 1. Improper designed chairs, work stations, 2. In-adequate sitting arrangement & storage | 1. Pain in wrist, shoulders and back, 2. Lack of Concentration, 3. Low productivity | 3 | 2 | 6 | N | L | A |  | Assess ergonomic & work facilities thru a survey.
d | Water supplly in the office | Contamination water (may be at source or at water tank or improper maintenance of water purifier) | Spread of various water related disease | 4 | 2 | 8 | N | M | UA |  | Develop a mechanism for water quality monitoring
e | Using VDU (Computer) | Ionizing and non-ionizing radiation | Eye strain | 3 | 2 | 6 | N | L | A |  | Simple exercise tips to be prepared & circulated for eye strain
f | Storage & disposal of office waste | Improper storage & disposal of 1. Used water bottle. 2. Paper & cartoons 3. Tissue Paper & other sanitary materials | 1. Accidental Fire, 2. Unhygienic condition | 3 | 3 | 9 | N | M | UA |  | A procedure to be developed for proper storage & disposal of solid waste
g | Office passage | Presence of unclear/unidentified passage and insufficient head room within office premises | Collision, head injury etc. | 3 | 3 | 9 | N | M | UA |  | identify obstructions including head room with in the office premises. Remove if possible else, put warning signs.
h | Electrical Installation | 1. Uninsulated cable and defective plug points 2. Improper earthing, 3. Overloading | Elecrical shock, burn injury, fire | 3 | 4 | 12 | Y | M | UA |  | Develop a mechanism for periodic inspection of electrical installations.
i | Filing/attending office work | Sharp metal parts like clips, knife, sharp edges of open drawers and filling cabinet | Cuts and bruises | 2 | 3 | 6 | Y | M | A
j | Floor Washing with the help of Chemicals (phenyl, ala, braso, thinner, hertel plus etc.) | Skin & eye contact with chemicals, inhalation of volatile organic compounds | skin irritation, damage to eyes and respiratory tract | 2 | 3 | 6 | N | L | A |  | Prepare and prcatice a guideline to create awareness regarding basic safety tips and use of PPE's during housekeeping work.
k | Floor wiping | 1. Wet floor 2. Intanglement with wiper | Slip, Trip & injury | 2 | 2 | 4 | N | L | A
2 | Canteen
a | Food preparation | 1. Inferior quality of food ingradients, 2. Improper cleaning & preparation of foods, 3. Unhygienic condition of cooking place, 4. Unhealthy condition of cook (Dirty hairs, nails & skin) and having communicable disease | 1. Food Poisioning, 2. Spread of disease | 3 | 3 | 9 | N | M | UA |  | Develop and establish a procedure for HSE requirements of Canteen & Pantry Service including quality of food ingradients, periodically medical check up for food handlers, proper storage & disposal of food & food wastage & proper potable drinking water facilities.
|  | Unsafe storage and use of LPG cylinders | Fire & Explosions | 4 | 2 | 8 | Y | M | UA |  | Develop and adminster a work instruction for safe handling of LPG cylinders
b | Food storage & disposal | 1. Un-hygienic storage of food 2. Un-hygienic storage & disposal of food wastage | 1. Spread of disease, 2. Bad smell & odour, | 3 | 3 | 9 | N | M | UA |  | Develop and establish a procedure for quality control of food & water during storgae, serving including safe storgae and disposal of food waste
c | Serving of food | Unhealthy condition of personnel serving the food | 1. Food poisoning, 2. Spread of disease | 3 | 3 | 9 | N | M | UA
d | Drinking Water Facility | Contamination may be at source, water tank or improper maintenance of water purifier. | Water borne diseases | 3 | 3 | 9 | Y | M | UA
3 | Provision of office logistics (Arrangement/ outsourcing of vehicles)
a | Drivers condition | 1. In-competent drivers , 2. Driver without valid licence, 3. Habit of drinking and driving or sleeping during driving | Accident/ injury | 4 | 2 | 8 | Y | M | UA |  | Develop and practice a guideline specifying the criteria for selection and engagement of travel agency.
b | Vehicle condition | 1. Vehicle not in proper running condition 2. Without brakes, horn, mirror etc, 3. Without PUC, Insurance etc. | 1. Un-comfortable, Body pain/ back pain, 2. Accident/injury 3. Legal actions | 3 | 3 | 9 | Y | M | UA
4 | Residential Quarter/Guest House
a | Electrical Installation | 1. Uninsulated cable and defective plug points 2. Improper earthing, 3. Overloading | Elecrical shock, burn injury, fire | 3 | 4 | 12 | Y | M | UA |  | Develop a mechanism for periodic inspection of electrical installations.
b | Water supply & Sanitation | 1. In-adequate Qty. of water, 2. Contaminated water, 3. Improper cleaning of toilets/bathrroms. | 1. Unhygienic condition 2. Water borne diseases | 3 | 4 | 12 | Y | M | UA
c | Waste collection & disposal | 1. Un-hygienic storage & disposal of food & other waste | 1. Spread of disease, 2. Bad smell & odour, | 3 | 3 | 9 | N | M | UA
d | Food perparation | Use of wood & coal | suffocation & other respiratory problems. | 3 | 3 | 9 | Y | M | UA
|  | Use of open heater | Elecrical shock, burn injury, fire | 4 | 3 | 12 | Y | M | UA
e | Uncontrolled entry/exit | Un-authorized person can entered. | Theft, fear and other security problems | 4 | 3 | 12 | Y | M | UA

## Concrete
Hazard Identification, Risk Assessment & Control Measures
Project: XXXXX |  |  | Section/Deptt.: Execution | [5 empty] | Date:
S. No. | Activity | Hazards (Conditions/Act) | Risk | Severity (S) | Probability (P) | SXP | Legal (Y/N) | Risk Level (H, M or L) | Risk Category (A/UA) | Control Measures
Shuttering/formwork
| Placing/Removal of formwork | 1. Use of defective tools (Hand/power tool) i.e. blunt hammer, saw, planner etc, 2. Use of defective sling /shackles/pulley. | Injury, electrocution etc | 4 | 2 | 8 | Y | M | UA
|  | 1. Working at height without platform, railing etc., 2. Improper access (defective ladders), 3. Working at height without safety belt/anchoring safety belt. 4. Unguarded floor opening & Unprotected slab edge | Fall of person lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA | Collpase of structure due to premature removal of forms.
|  | Working at height without safety net/safety fans. | Fall of object lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
|  | 1. Defective props or improper fixing of props (Not vertical, not tie with other members), 2. Defective jacks or improper fixing of jacks. 3. Inadequate bracing. | Collapse of form work lead to injury including fatalities. | 5 | 3 | 15 | Y | M | UA | Inadequate / unsafe design of staging/scaffolding system.
|  | Improper/akward posture/position due to lack of proper working platform | 1. May lead to fall from height 2. Back pain/body pain etc. | 3 | 3 | 9 | Y | M | UA
Placing of Concrete
a | Placing by Concrete Pump | 1. Unguarded moving parts, 2. Defective/choked concrete pipeline, 3. Unsupported pipeline, 4. Placing of pump on uneven ground, 5. In-competent operator | Inadvertent operation of pump lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA | Pipeline corroded from inside.
|  | Exposure to Noise | 1. Noise induced hearing loss, (Occupational Disease) 2. lack of concentration, irritation lead to accident. | 2 | 3 | 6 | Y | L | UA | Falling / spilling over of concrete leading to injury to persons.
|  | 1. Unsafe placing of Transit Mixer i.e unevn ground, without stopper etc. 2. Unattandent in running condition. | Uncontrolled movement lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
|  | Exposure to wet concrete | Dermatitis (Skin Diseases), Skin burn etc. (Occupational Disease) | 3 | 3 | 9 | Y | M | UA
|  | 1.Placing of concrete at height without platform, railing etc., 2. Improper access (defective ladders), 3. Working at height without safety belt/anchoring safety belt. 4. Unguarded floor opening & Unprotected slab edge | Fall of person lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
b | Manual Placing | 1.Placing of concrete at height without platform, railing etc., 2. Improper access (defective ladders), 3. Working at height without safety belt/anchoring safety belt. 4. Unguarded floor opening & Unprotected slab edge | Fall of person lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
|  | Working at height without safety net/safety fans. | Fall of object lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
|  | Exposure to wet concrete/Spillage of concrete | Dermatitis (Skin Diseases), Skin burn etc. | 2 | 3 | 6 | Y | L | A
Pre-stress Concrete
a | Shifting and Placement & de-coiling of material High Tension Wire | Elastic Energy Release | Bodily Injuries leading to permanent disablement | 4 | 2 | 8 | Y | M | UA
b | Cutting of H.T wire with grinder | Flying chips | Eye injury | 3 | 3 | 9 | Y | M | UA
c | Lifting and threading of H.T wire | 1. Heavy weight and sharp edges, 2. Lifting of strands without proper anchoring and positioning of sling belts | Personal injuries | 3 | 2 | 6 | Y | L | UA
d | Handling and erection of Jacks | Inappropriate holding /positioning of the jack during stressing of tendons | Personal injuries | 4 | 2 | 8 | Y | M | UA
e | Pre-stressing | 1. Breaking of cables/ Hydraulic Hose 2. Workmen positioned exactly towards the direction of the jacking force | Personal injuries | 5 | 2 | 10 | Y | M | UA
f | Grouting | 1. Unguarded machinery 2. Flying particles | Personal injuries | 3 | 2 | 6 | Y | L | A
Vibration
a | Vibration by needle vibrator | 1. Unguarded moving parts, 2. Defective needle 3. Placing of vibrator on uneven ground, 4. In-competent operator | Inadvertent operation of vibrator lead to accident/injury. | 3 | 3 | 9 | Y | M | UA
|  | Exposure to Noise | 1. Noise induced hearing loss, (Occupational Disease) 2. lack of concentration, irritation lead to accident. | 2 | 3 | 6 | Y | L | A
|  | Exposure to Vibration | 1. White finger, (Occupational Disease) 2. lack of concentration, irritation lead to accident. | 3 | 3 | 9 | Y | M | UA
b | Vibration by plate vibrator | 1. Unguarded moving parts, 2. Placing of vibrator on uneven ground, 3. In-competent operator | Inadvertent operation of vibrator lead to accident/injury. | 3 | 3 | 9 | Y | M | UA
|  | Exposure to Noise | 1. Noise induced hearing loss, (Occupational Disease) 2. lack of concentration, irritation lead to accident. | 3 | 2 | 6 | Y | L | A
|  | Exposure to Vibration | 1. White finger, (Occupational Disease) 2. lack of concentration, irritation lead to accident. | 3 | 3 | 9 | Y | M | UA
Curing
a | Curing by Pump | 1. Unguarded moving parts, 2. Defective electric cable & connection 3. In-competent operator, 4. Defective pipeline | Lead to accident/injury & electrocution. | 3 | 3 | 9 | Y | M | UA
|  | 1. Curing at height without platform, railing etc., 2. Improper access (defective ladders), 3. Curing at height without safety belt/anchoring safety belt. 4. Unguarded floor opening & Unprotected slab edge | Fall of person lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
b | Manual Curing | 1. Curing at height without platform, railing etc., 2. Improper access (defective ladders), 3. Curing at height without safety belt/anchoring safety belt. 4. Unguarded floor opening & Unprotected slab edge 5. Exposure to curing compound | 1. Fall of person lead to injury including fatality. 2. Respiratory problems, Skin effects due to chemical compound. | 3 | 3 | 9 | Y | M | UA

## Batching Plant
Hazard Identification, Risk Assessment & Control Measures
Project: XXXXX |  |  | Section/Deptt.: Execution | [5 empty] | Date:
S. No. | Activity | Hazards (Conditions/Act) | Risk | Severity (S) | Probability (P) | SXP | Legal (Y/N) | Risk Level (H, M or L) | Risk Category (A/UA) | Control Measures
Batching Plant
a | Plant Condition | 1. Unguarded moving parts, 2. Inadequate working platform, 3. Absence of safety devices (limit swiches, pull card, emergency stop switch etc.) 4. In-competent operator | 1. Inadvertent operation of plant lead to injury including fatality 2. Absence of safety devices could lead to accident/injury during operartion. | 4 | 2 | 8 | Y | M | UA
b | Plant operation | Exposure to cement dust | 1. Lung Disease (Occupational Disease) 2. Irritation to respiratory tract | 3 | 3 | 9 | Y | M | UA
|  | Exposure to wet concrete | Dermatitis (Skin Diseases), Skin burn etc. (Occupational Disease) | 3 | 3 | 9 | Y | M | UA
|  | Uncontrolled movement of vehicles (Tippers/Loader) | May hit the workmen lead to injury. | 3 | 3 | 9 | Y | M | UA
|  | Hopper without screen | Fall of person inside hopper lead to injury including fatality. | 4 | 2 | 8 | Y | M | UA
|  | 1. Working at height without platform, railing etc., 2. Improper access (defective ladders), | Fall of person lead to injury including fatality. | 3 | 3 | 9 | Y | M | UA
|  | Exposure to noise | 1. Noise induced hearing loss, (Occupational Disease) 2. lack of concentration irritation lead to accident. | 3 | 3 | 9 | Y | M | UA
|  | Unsafe electrical connections i.e. defective & irregular cable route, improper earthing, unprotected/uncovered switch panel etc. | Electrocution | 3 | 3 | 9 | Y | M | UA
c | Plant maintenance | 1 Maintenance without stopping the plant, 2. Un-authorised mechanic for maintenance, 3. Mal functioning of limit swiches 4. Maintenance without follow lockout/tag out procedure. | Lead to accident/injury including fatality. | 3 | 3 | 9 | Y | M | UA

## Fabrication
Hazard Identification, Risk Assessment & Control Measures
Project: XXXXX |  |  | Section/Deptt.: Fabrication Yard | [5 empty] | Date:
S. No. | Activity | Hazards (Conditions/Act) | Risk | Severity (S) | Probability (P) | SXP | Legal (Y/N) | Risk Level (H, M or L) | Risk Category (A/UA) | Control Measures
a | Bar cutting | 1. Improper placing of rod on cutting machine | Deflaction of rod may hit the operator leading to injury | 3 | 3 | 9 | N | M | UA | Appointment of competent person. Providing awareness & training
|  | 2. Uneven & slippery surface near bar cutting area due to oil, mud, water | Slip & fall of person leading to injury | 3 | 3 | 9 | N | M | UA | Ensure even and dry surface.
|  | 3. Improper stacking of material | Fall of material & person leading to injury | 3 | 3 | 9 | N | M | UA | Proper practice for stacking of material & good house keeping
|  | 4. Loose electrical connections/ loss of insulation/ no earthing protection | Short circuit, electric shock, flash burn & fire leading to injury/ fatality | 4 | 3 | 12 | Y | M | UA
b | Bar bending | 1. Improper placing of rod for bending | Deflaction of rod may hit the operator leading to injury | 3 | 3 | 9 | N | M | UA | Appointment of competent person. Providing awareness & training
|  | 2. Slippery surface near bar bending area due to oil, mud, water | Slip & fall of person leading to injury | 3 | 3 | 9 | N | M | UA | Even and dry surface.
|  | 3. Improper stacking of material | Fall of material & person leading to injury | 3 | 3 | 9 | N | M | UA | Proper practice for stacking of material & good house keeping
c | Arc welding | 1. Exposure to radiation | Welder's cataract/ red eye | 2 | 4 | 8 | N | M | UA | Use welding shield/ goggles
|  | 2. Contact with hot splinters/ slag | Burn injury | 2 | 4 | 8 | N | M | UA | Fire proof apron/ gloves/ screen
|  | 3. Loose connections/ loss of insulation/ no earthing protection | Electric shock, flash burn & fire leading to injury/ fatality | 4 | 3 | 12 | Y | M | UA | Proper maintenance of the plant, use shockproof boots and hand gloves Ensure that functional earthing is provided
|  | 4. Presence of flammable material nearby | Fire/ explosion causing fatality | 4 | 4 | 16 | N | H | UA | No flammable material to be allowed nearby. Keeping fire extinguisher (DCP/ CO2)
|  | 5. Exposure to fumes | Irritation, lung disease | 3 | 3 | 9 | N | M | UA | Adequate ventilation. Ensure use of gas masks.
|  | 6. Poor ventilation, in case of cofined space | Asphyxiation leading to fatality | 4 | 3 | 12 | Y | M | UA | Work permit system. Ensure adequate ventilation.
d | Grinding | 1. Breaking of wheel | Body injury | 3 | 3 | 9 | Y | M | UA | Correct mounting of wheel with guard. Check condition of wheel by suitable method Donot run the wheel exceeding the wheel rpm Ensure proper storage of wheels
|  | 2. Flying of chips | Eye/body injury | 3 | 3 | 9 | Y | M | UA | Ensure use of wear safety googles and appron Ensure that the guards are in place
|  | 3. Generation of noise | Noise induced hearing loss, threshold shift | 3 | 3 | 9 | Y | M | UA | Ensure use of ear Ear plug/ muff
|  | 4. Generation of dust | Lung disease, suffocation | 3 | 3 | 9 | Y | M | UA | Ensure use of dust mask
|  | 5. Entanglement of loose clothing | Injury | 3 | 3 | 9 | Y | M | UA | No loose clothings should be weared while working on griding machine
|  | 6. Uninsulated grinder causing electrical shock | Electrical burns/ electric shok leading to injury/ fatality | 4 | 3 | 12 | Y | M | UA
|  | 7. unsafe gap between the tool rest and wheel surface | Traping of finger leading to injury/ amputation | 3 | 3 | 9 | Y | M | UA | Ensure that the distance between wheel surface and work rest is not more then 0.3mm
e | Gas cutting | 1. Damaged hose pipes/ cutting torch | Leakage of gas leading to fire | 3 | 3 | 9 | Y | L |  | Always check the hose pipe,cutting torch and regulator before use.
|  | Exposure to fumes | Respiratory problem, lung disease, irritation of eyes | 5 | 3 | 15 | Y | H |  | Ensure use of gas mask Ensure adequate ventilation at the work place
|  | Exposure to spark | Eye injury | 2 | 4 | 8 | Y | M |  | Ensure the use of safety googles
|  | 4. Flash back to gas cylinders | Fire & explosion leading to injury/ fatality | 5 | 4 | 20 | Y | H |  | Provision of flash back arrestor, regulator. Also provide fire extinguisher on cutting set trolley Ensure good condition of hose and cutter
|  | 5. Exposure to hot flames | Burns in hands/ Injury | 3 | 2 | 6 | Y | L |  | Ensure use of hand gloves
|  | 6. Damaged pressure guage/ excess pressure of acetylene | Back fire leading to major injuries / fatality | 5 | 3 | 15 | Y | H |  | Ensure working condition of pressure guage Acetylene pressure should not exceed 15PSI
f | Use of electricity operated portable hand tools | 1. Unsafe operation/ improper method of using tool | Injury/ amputation | 3 | 3 | 9 | N | M | UA | Appointment of competent person. Providing awareness & training
|  | 2. Badly maintained & poor storage of tools | Injury/ amputation | 2 | 4 | 8 | N | M | UA | Develop & follow good pratice of maintenance & store of tools. Providing awareness & training
|  | 3. Exposure to vibration | Hand arm vibration syndrome, white fingers | 2 | 4 | 8 | N | M | UA | Ensure use of less vibrating tools. Job rotation of workers. Provide frequent breaks in between work. Use of vibration resistant hand gloves.
|  | 4. Loose electrical connections/ poor quality cables/ poor insulation/ no earthing protection | Flash burn, shock causing injury/ fatality | 3 | 4 | 12 | Y | M | UA
|  | 5. Exposure to noise | Noise induced hearing loss, threshold shift | 2 | 5 | 10 | N | M | UA | Ensure use of Ear Plugs/ Muffs. Job rotation wherever possible. Conduct periodic audiometric test of workers.
|  | 6. Exposure to dust | Suffocation, lung disease | 2 | 5 | 10 | N | M | UA | Ensure use of dust mask. Ensure adequate ventilation. Job rotation wherever possible.
g | Carpentry work | 1. Unsafe operation/ improper method of using tool | Injury/ amputation | 3 | 3 | 9 | N | M | UA | Appointment of competent person. Providing awareness & training
|  | 2. Badly maintained & poor storage of tools | Injury/ amputation | 2 | 4 | 8 | N | M | UA | Develop & follow good pratice of maintenance & store of tools. Providing awareness & training

## Road
Hazard Identification, Risk Assessment & Control Measures
Project: XXXXX |  |  | Section/Deptt.: | [5 empty] | Date:
S. No. | Activity | Hazards (Conditions/Act) | Risk | Severity (S) | Probability (P) | SXP | Legal (Y/N) | Risk Level (H, M or L) | Risk Category (A/UA) | Control Measures
a | Site Preparation/ Leveling (Operation of Grader/ Excavater/ Loader) | 1. Presence of unauthorised person in the work zone | Striking by the equipment leading to injury | 3 | 3 | 9 | N | M | UA | Prohibit the entry of unauthorized persons in the working area
|  | 2. Incompetent operator/ Unauthorized Operation | Accident and injury | 3 | 3 | 9 | Y | M | UA | Ensure deplyment of compent operator with valid license Heavy Equipment operation. Establish mechanism to prevent operation by unauthorised person.
|  | 3. Inoperative/ no safety devices (e.g. reverse horn, reverse light, etc.) with Grader/ Excavator /Loader | Injury to person while reversing | 4 | 4 | 16 | Y | M | UA | Driver should be provided with a trained banks man where necessary. Provide Reverse alarm
|  | 4. Inadequate Illumination | Injury to person due to accident | 3 | 3 | 9 | Y | M | UA | Ensure Proper Illumination (100 LUX)
|  | 5. Exposure to dust | Lung Disease (Silicosis) Irritation of respiratory tract | 3 | 3 | 9 | Y | M | UA | Provide dust mitigation measures such as sprinklings of water. Ensure use of Dust Mask
|  | 6. Use of defective/ poorly maintained grader/ excavator/ loader. | Failure/ lack of control in operation lead to accident/ injury | 3 | 3 | 9 | Y | M | UA | Ensure preventive maintenance.
|  | 7. Working near traffic | Accident and injury | 4 | 3 | 12 | Y | M | UA | Adopt Traffic Safety Rules
b | Dumping, Laying, Grading and Compaction | Unsafe reversing of the vehicles. Improper communication between the driver and helper/ bank men | Striking, overrun, trapping causing severe injury/fatality | 4 | 4 | 16 | Y | M | UA | Trained Bank men shall be deployed at all dumping sites Functional reverse horn to provided Un-authorized persons and visitor should not be allowed with in the critical area Periodic training to drivers, helpers, bank men and flag man
|  | Entering onto the live roads | Striking, overrun, trapping causing severe injuries | 4 | 3 | 12 | Y | M | UA | Trained Flag boys and warning systems should be provided. Use of reflective jacket Sign boards at appropriate intervals as per the IRC SP 55
c | Curb Construction | live roads | Striking, overrun, trapping causing severe injuries | 4 | 3 | 12 | Y | M | UA | Trained Flag boys and warning systems should be provided. Use of reflective jacket Sign boards at appropriate intervals as per the IRC SP 55
|  | Kerb Cutting | Injury | 3 | 3 | 9 | Y | M | UA | Proper foot wear and Proper Supervision
|  | Untrained Operators | Injury to the operator, others | 3 | 3 | 9 | Y | M | UA | Proper supervision Trained operators
d | Brooming | Exposure to dust | Irritation to the respiratory track Lung diseases | 3 | 3 | 9 | Y | M | UA | Water Sprinkling Use of dust mask
e | Paver Operation | Blocked operator vision | May lead to an accident, injury | 3 | 3 | 9 | Y | M | UA | Ensure the maximum unrestricted view of the operating area. Trained signaler must be deployed to guide the Operator
|  | Slippery platform due to oil, grease, etc. Obstruction in platform. | Slip/ fall of person laeding to injury. | 3 | 3 | 9 | Y | M | UA | Ensure that the operating platforms remain free from oil, grease & other obstruction. Arrest leaks if any.
|  | Working near hopper or rotating parts while machine is in running condition. | Entanglement with the rotating part of m/c leading to serious injury/ amputation/ abrasion | 3 | 3 | 9 | Y | M | UA | Do not attempt to remove paving material from the hopper, screed extensions or auger area while the machine is running. Avoid loose clothing. Ensure that the guards are in place.
|  | Working near the screed while it is being raised or lowered. | Injury | 3 | 3 | 9 | Y | M | UA | Keep well away from the screed when it is being raised or lowered.
|  | Carrying out maintenance while machine is running | Entanglement with the rotating part of m/c leading to serious injury/ amputation/ abrasion | 3 | 3 | 9 | Y | M | UA | Servicing, adjustments & repairs must only be carried out when the machine is stationary. Use of interlocks to be done wherever possible Experienced and trained personnel should do maintenance work
|  | Inspection of raised screed without proper support | Sudden fall of screed & human injury | 3 | 3 | 9 | Y | M | UA | When the screed is raised for inspection, cleaning or maintenance ensure that the screed support cables are in position
|  | Disconnecting pressurized hydraulic lines. | Injury due to pressurized fluids | 3 | 3 | 9 | Y | M | UA | Before disconnecting the hydraulic lines, relieve all pressure in the system.
|  | Parking of the Paver on road | Vehicle collision during night | 3 | 3 | 9 | Y | M | UA | Proper security arrangements. Vehicle reflectors to be used. Safety cones to be used. Warning signs boards and signals should be used.
|  | live traffic | Striking, overrun, trapping causing severe injuries | 4 | 3 | 12 | Y | M | UA | Trained Flag boys and warning systems should be provided. Use of reflective jacket. Sign boards at appropriate intervals as per the IRC SP 55.